## Sheet1
Stage | Census Stage | Activities | Census - 4 Years |  |  |  | Census - 3 Years |  |  |  | Census - 2 Years |  |  |  | Census - 1 Year |  |  |  | Census Year |  |  |  | Census + 1 Year |  |  |  | Census + 2 Years |  |  |  | D+3 thru 5 Years
|  |  | Example 2016 |  |  |  | Example 2017 |  |  |  | Example 2018 |  |  |  | Example 2019 |  |  |  | Example Census Date July 1, 2020 |  |  |  | Example 2021 |  |  |  | Example 2022 |  |  |  | Example 2023 to 2025
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Preparatory stage | Census Planning | Setting strategic objectives for the entire census programme | bar: Example 2016 Q1 to Example 2016 Q4
Overall census planning | bar: Example 2016 Q4 to Example 2017 Q3
Statistical capacity assessment | bar: Example 2017 Q1 to Example 2017 Q4
Plan for enumeration | bar: Example 2017 Q4 to Example 2018 Q1
Risk assessment and contingency plan | bar: Example 2018 Q1 to Example 2018 Q4
Convening government stakeholders | bar: Example 2018 Q1 to Example 2018 Q4
Plan for public relations | bar: Example 2018 Q3 to Example 2018 Q4
Plan for data processing | bar: Example 2018 Q3 to Example 2018 Q4
Plan for post-enumeration survey | bar: Example 2019 Q1 to Example 2019 Q2
Plan for recruiting and training enumeaors | bar: Example 2019 Q3 to Example 2019 Q4
| Preparation | Census legislation | bar: Example 2017 Q1 to Example 2017 Q4
Organization of Commissions and Committees | bar: Example 2017 Q3 to Example 2018 Q4
Administrative organization and management structure | bar: Example Census Date July 1, 2020 Q1 to Example Census Date July 1, 2020 Q3
Consultation with users | bar: Example 2016 Q3; Example 2017 Q3; Example 2018 Q3; Example 2019 Q3
Contracting out | bar: Example 2018 Q1 to Example 2021 Q4
Communication and publicity strategies | bar: Example 2019 Q1 to Example 2019 Q4
Difinition of censeus theme | bar: Example 2017 Q1 to Example 2017 Q4
Census calendar | bar: Example 2017 Q2 to Example 2017 Q3
Financial management | bar: Example 2016 Q1 to Example 2022 Q3
Procurement | bar: Example 2017 Q3 to Example Census Date July 1, 2020 Q2
Use of technology | bar: Example 2017 Q1 to Example 2019 Q4
Quality assurance | bar: Example 2017 Q1 to Example 2019 Q4
| Enumeration Area Delineation | Identofying number of households by small area | bar: Example 2018 Q4 to Example 2019 Q1
Demarkation of EA boundry | bar: Example 2019 Q1 to Example 2019 Q2
| Mapping | Decision on technology and method | bar: Example 2017 Q1 to Example 2017 Q4
Procurement of census mapping equipment | bar: Example 2018 Q1 to Example 2018 Q2
Gathering point data, satellite imagery | bar: Example 2018 Q3 to Example 2018 Q4
Recruiting GIS staff | bar: Example 2018 Q3 to Example 2018 Q4
Creating a GIS database | bar: Example 2018 Q4 to Example 2019 Q1
Verifying | bar: Example 2018 Q4 to Example 2019 Q1
Printing base maps and EA maps | bar: Example 2019 Q4 to Example Census Date July 1, 2020 Q1
| Questionnaire development | Selection of topics | bar: Example 2017 Q4 to Example 2019 Q3
Form design and testing | bar: Example 2019 Q1 to Example 2019 Q3
Consultation with users | bar: Example 2017 Q2; Example 2018 Q2; Example 2019 Q2
Development of census tabulatin and analysis plan | bar: Example 2019 Q1 to Example 2019 Q4
| Manuals development | Manual for enumerators | bar: Example 2018 Q1 to Example 2019 Q4
Manual for supervisors | bar: Example 2019 Q1 to Example 2019 Q4
Manual for editors | bar: Example 2019 Q3 to Example Census Date July 1, 2020 Q1
| Pre-test and pilot census | Selection of areas to be covered | bar: Example 2017 Q1; Example 2018 Q1; Example 2019 Q1
Printing of draft questionnaires and manuals | bar: Example 2017 Q2; Example 2018 Q2; Example 2019 Q2
Recruitment and training of field staff | bar: Example 2017 Q2; Example 2018 Q2; Example 2019 Q2
Field enumeration in the selected areas | bar: Example 2017 Q3; Example 2018 Q3; Example 2019 Q3
Data processing (coding, data entry, tabulations) | bar: Example 2017 Q3; Example 2018 Q3; Example 2019 Q3
Analyses and evaluation of data and information | bar: Example 2017 Q4; Example 2018 Q4; Example 2019 Q4
Preparation of the detailed report | bar: Example 2017 Q4; Example 2018 Q4; Example 2019 Q4
Census stage | Setting up field operations | Printing of the final versions of questionnaires and manuals | bar: Example 2019 Q4 to Example Census Date July 1, 2020 Q1
Procurement of census furniture and other materials | bar: Example 2019 Q4 to Example Census Date July 1, 2020 Q1
Census homepage | bar: Example 2019 Q4 to Example Census Date July 1, 2020 Q1
Toll-free service | bar: Example Census Date July 1, 2020 Q1
Logistics for census materials | bar: Example Census Date July 1, 2020 Q1 to Example Census Date July 1, 2020 Q2
Distribution of supplies on the field | bar: Example Census Date July 1, 2020 Q1 to Example Census Date July 1, 2020 Q2
Recruiting and training supervisors | bar: Example Census Date July 1, 2020 Q1 to Example Census Date July 1, 2020 Q2
Recruiting and training enumeaors | bar: Example Census Date July 1, 2020 Q1 to Example Census Date July 1, 2020 Q2
Public relations campaigns | bar: Example 2019 Q4 to Example Census Date July 1, 2020 Q2
| Enumeration | Preparatory survey | bar: Example Census Date July 1, 2020 Q2
Field enumeration | bar: Example Census Date July 1, 2020 Q3
Assembling of questionnaires and other field materials | bar: Example Census Date July 1, 2020 Q3
Field editing | bar: Example Census Date July 1, 2020 Q3
Return of questionnaires and materials | bar: Example Census Date July 1, 2020 Q3
Post-census stage | Post-enumeation surey | Design of the PES questionnaires and manuals | bar: Example Census Date July 1, 2020 Q1
Printing of the PES questionnaires & manuals | bar: Example Census Date July 1, 2020 Q2
Drawing of the sample EAs by cluster for the PES | bar: Example Census Date July 1, 2020 Q1
Recruitment and training of field staff | bar: Example Census Date July 1, 2020 Q2
Distribution of materials and placement of staff on the field | bar: Example Census Date July 1, 2020 Q2
Post Enumeration Survey (Data collection in the sampled Eas) | bar: Example Census Date July 1, 2020 Q3
Analyses and evaluation of coverage of the census/Correction factors | bar: Example Census Date July 1, 2020 Q4 to Example 2021 Q1
| Data processing | Processing strategies | bar: Example 2018 Q1 to Example 2018 Q4
Procurement of census data processing equipment | bar: Example 2018 Q1 to Example 2019 Q2
Location of processing centres | bar: Example Census Date July 1, 2020 Q3
Establishing the workforce structure and recruiting staff | bar: Example Census Date July 1, 2020 Q2 to Example Census Date July 1, 2020 Q3
Processing operations | bar: Example Census Date July 1, 2020 Q3 to Example 2021 Q2
Coding | bar: Example Census Date July 1, 2020 Q3 to Example Census Date July 1, 2020 Q4
Edit & Imputation | bar: Example Census Date July 1, 2020 Q4 to Example 2021 Q2
Weighting | bar: Example 2021 Q2
| Relese of results | Preliminary results | bar: Example Census Date July 1, 2020 Q4
Provisinal Census results | bar: Example 2021 Q3
Final census results | bar: Example 2021 Q4 to Example 2022 Q3
| Census products | Broad product strategy | bar: Example 2019 Q1 to Example 2019 Q4
Printed reports | bar: Example 2022 Q2 to Example 2022 Q4
Public use sample data | bar: Example 2022 Q4
Individual data | bar: Example 2022 Q4
CD and on-line
| Dissemination | Dissemination strategy | bar: Example 2021 Q1 to Example 2021 Q4
User consultation | bar: Example 2019 Q2; Example Census Date July 1, 2020 Q2; Example 2021 Q2; Example 2022 Q2
| Documentation and archiving | Documenting census operations | bar: Example 2022 Q1 to Example 2022 Q2
Archiving individual census records | bar: Example 2021 Q3 to Example 2022 Q1
| Evaluation | Process quality | bar: Example Census Date July 1, 2020 Q4 to Example 2021 Q2
Data quality | bar: Example 2021 Q2 to Example 2021 Q4
| Utilization | Use of small area data | bar: Example 2021 Q2 to Example 2021 Q4; Example 2023 to 2025 Q1 to Example 2023 to 2025 Q4
Cross-cutting and emerging social issues | bar: Example 2021 Q2 to Example 2021 Q4; Example 2023 to 2025 Q1 to Example 2023 to 2025 Q4
Promotion of, and training on, uses of census data | bar: Example 2023 to 2025 Q1 to Example 2023 to 2025 Q4